## Summary
SUMMARY
Units Commissioned upto 31.8.2017
| Category | Capacity (MW) | No. of Units
| FGD not possible | 2979 | 20
| FGD being explored | 0 | 0
| FGD Planned | 34505 | 92
| Sox Compliant | 0 | 0
| FGD Installed | 1320 | 2
| CFBC Boiler | 2030 | 22
| Retirement | 1934 | 17
| Total | 42768 | 153
| ESP PHASING | 2030 | 22
| ESP |  |  | FGD
| YEAR-WISE PHASING PLAN |  |  | YEAR-WISE PHASING PLAN
| YEAR | Capacity | Units | YEAR | Capacity | Units
| 2019 | 250 | 2 | 2019 | 0 | 0
| 2020 | 0 | 0 | 2020 | 3680 | 7
| 2021 | 720 | 12 | 2021 | 5770 | 13
| 2022 | 540 | 4 | 2022 | 6675 | 17
| 2023 | 270 | 2 | 2023 | 15960 | 50
| 2024 | 0 | 0 | 2024 | 600 | 2
| Under Closure | 250 | 2 | NO PLAN | 1820 | 3
| Total | 2030 | 22 | Total | 34505 | 92
Description of worksheets contained in the workbook
1 | Total | Total coal/ Lignite based capacity in the region captured from the CEA database. Any left out unit may inform and to be included in the plan.
2 | Retirement | Units either retired or identified for retirement which are not included in the analysis
3 | CFBC | Units equiped with CFBC boilers and are likely to meet Sox norms
4 | FGD Installed | Units with FGD already installed and are likely to meet Sox norms
5 | Sox compliant | Units which have claimed to be Sox compliant which is unlikely. Generators may confirm or give phasing plan for FGD.
6 | FGD planned | Units for which FGD implementation plan has been prepared/ to be prepared
7 | FGD being explored | Units where studies for FGD installation being done. May confirm about the final decision.
8 | FGD not possible | Units where FGD installation is not possible
9 | ESP phasing | ESP phasing plan (excudes units whch cannot become Sox compliant. The phasing plan for ESP upgraadtion for units which are installing FGD shall be the same as for FGD)

## Total
Sr. No. | Developer | Name of Project | Sector | State | Region | Prime Mover | Unit No | Total Capacity | DT-of COMMISSIONING | Age in years | Type of Fuel | Whether FGD Installed | Whether CFBC | Whether ESP retrofit required | Identified for retirement | Phasing Plan for Implementation | Phase out plan | Comments of GM Division
1 | IPGCL | RAJGHAT TPS | State Sector | Delhi | NR | Steam | 1 | 67.5 | 1989-03-10 | 28.3068 | COAL | N | N | Y | Y |  |  | IDENTIFIED FOR RETIREMENT
2 | IPGCL | RAJGHAT TPS | State Sector | Delhi | NR | Steam | 2 | 67.5 | 1990-02-20 | 27.3562 | COAL | N | N | Y | Y |  |  | IDENTIFIED FOR RETIREMENT
3 | NTPC | BADARPUR TPS | Central Sector | Delhi | NR | Steam | 1 | 95 | 1973-07-26 | 43.9397 | COAL | N | N | Y | Y |  | 31/07/2018 | IDENTIFIED FOR RETIREMENT
4 | NTPC | BADARPUR TPS | Central Sector | Delhi | NR | Steam | 2 | 95 | 1974-08-05 | 42.9123 | COAL | N | N | Y | Y |  | 31/07/2018 | IDENTIFIED FOR RETIREMENT
5 | NTPC | BADARPUR TPS | Central Sector | Delhi | NR | Steam | 3 | 95 | 1975-03-29 | 42.2658 | COAL | N | N | Y | Y |  | 31/07/2018 | IDENTIFIED FOR RETIREMENT
6 | NTPC | BADARPUR TPS | Central Sector | Delhi | NR | Steam | 4 | 210 | 1978-12-02 | 38.5836 | COAL | N | N | N |  |  | 31/07/2018 | TO BE PHASED OUT
7 | NTPC | BADARPUR TPS | Central Sector | Delhi | NR | Steam | 5 | 210 | 1981-12-25 | 35.5178 | COAL | N | N | N |  |  | 31/07/2018 | TO BE PHASED OUT
8 | CHINA LIGHT POWER | MAHATMA GANDHI TPS | Private Sector | Haryana | NR | Steam | 1 | 660 | 2012-01-12 | 5.4493 | COAL | Y | N | N |  |  |  | FGD INSTALLED
9 | CHINA LIGHT POWER | MAHATMA GANDHI TPS | Private Sector | Haryana | NR | Steam | 2 | 660 | 2012-04-11 | 5.2027 | COAL | Y | N | N |  |  |  | FGD INSTALLED
10 | HGPCorpn | PANIPAT TPS | State Sector | Haryana | NR | Steam | 5 | 210 | 1989-03-28 | 28.2575 | COAL | N | N | N |  |  | 31/12/2018 | TO BE PHASED OUT
11 | HGPCorpn | PANIPAT TPS | State Sector | Haryana | NR | Steam | 6 | 210 | 2001-03-31 | 16.2411 | COAL | N | N | N |  | 30/06/2023 |  | FGD POSSIBLE
12 | HGPCorpn | PANIPAT TPS | State Sector | Haryana | NR | Steam | 7 | 250 | 2004-09-28 | 12.7425 | COAL | N | N | Y |  | 30/06/2023 |  | FGD POSSIBLE
13 | HGPCorpn | PANIPAT TPS | State Sector | Haryana | NR | Steam | 8 | 250 | 2005-01-28 | 12.4082 | COAL | N | N | Y |  | 30/06/2023 |  | FGD POSSIBLE
14 | HGPCorpn | RAJIV GANDHI TPS | State Sector | Haryana | NR | Steam | 1 | 600 | 2010-03-31 | 7.2356 | COAL | N | N | Y |  | 30/06/2023 |  | FGD POSSIBLE
15 | HGPCorpn | RAJIV GANDHI TPS | State Sector | Haryana | NR | Steam | 2 | 600 | 2010-10-01 | 6.7315 | COAL | N | N | Y |  | 31/03/2023 |  | FGD POSSIBLE
16 | HGPCorpn | YAMUNA NAGAR TPS | State Sector | Haryana | NR | Steam | 1 | 300 | 2007-11-01 | 9.6493 | COAL | N | N | Y |  | 31/12/2024 |  | FGD POSSIBLE
17 | HGPCorpn | YAMUNA NAGAR TPS | State Sector | Haryana | NR | Steam | 2 | 300 | 2008-03-29 | 9.2411 | COAL | N | N | Y |  | 31/12/2024 |  | FGD POSSIBLE
18 | NTPC | INDIRA GANDHI STPP | Central Sector | Haryana | NR | Steam | 1 | 500 | 2010-10-31 | 6.6493 | COAL | N | N | Y |  | 30/09/2021 |  | FGD POSSIBLE
19 | NTPC | INDIRA GANDHI STPP | Central Sector | Haryana | NR | Steam | 2 | 500 | 2011-11-05 | 5.6356 | COAL | N | N | Y |  | 30/06/2021 |  | FGD POSSIBLE
20 | NTPC | INDIRA GANDHI STPP | Central Sector | Haryana | NR | Steam | 3 | 500 | 2012-11-07 | 4.6274 | COAL | N | N | Y |  | 30/06/2021 |  | FGD POSSIBLE
21 | GVK Power Ltd. | GOINDWAL SAHIB | Private Sector | Punjab | NR | Steam | 1 | 270 | 2016-02-14 | 1.3562 | COAL | N | N | N |  | 30/06/2020 |  | FGD POSSIBLE
22 | GVK Power Ltd. | GOINDWAL SAHIB | Private Sector | Punjab | NR | Steam | 2 | 270 | 2016-03-15 | 1.274 | COAL | N | N | N |  | 31/03/2020 |  | FGD POSSIBLE
23 | L&T Power Development LTD(Nabha) | Nabha TPP (Rajpura TPP) | Private Sector | Punjab | NR | Steam | 1 | 700 | 2014-01-24 | 3.4137 | COAL | N | N | N |  | 31/03/2023 |  | FGD POSSIBLE
24 | L&T Power Development LTD(Nabha) | Nabha TPP (Rajpura TPP) | Private Sector | Punjab | NR | Steam | 2 | 700 | 2014-07-06 | 2.9671 | COAL | N | N | N |  | 31/12/2021 |  | FGD POSSIBLE
25 | PSEB | GH TPS (LEH.MOH.) | State Sector | Punjab | NR | Steam | 1 | 210 | 1997-12-29 | 19.4959 | COAL | N | N | Y |  | 31/12/2022 |  | FGD POSSIBLE
26 | PSEB | GH TPS (LEH.MOH.) | State Sector | Punjab | NR | Steam | 2 | 210 | 1998-10-16 | 18.6986 | COAL | N | N | Y |  | 30/06/2022 |  | FGD POSSIBLE
27 | PSEB | GH TPS (LEH.MOH.) | State Sector | Punjab | NR | Steam | 3 | 250 | 2008-01-03 | 9.4767 | COAL | N | N | Y |  | 31/03/2023 |  | FGD POSSIBLE
28 | PSEB | GH TPS (LEH.MOH.) | State Sector | Punjab | NR | Steam | 4 | 250 | 2008-07-31 | 8.9014 | COAL | N | N | Y |  | 31/03/2023 |  | FGD POSSIBLE
29 | PSEB | GND TPS(BHATINDA) | State Sector | Punjab | NR | Steam | 1 | 110 | 1974-09-22 | 42.7808 | COAL | N | N | N | Y |  |  | IDENTIFIED FOR RETIREMENT
30 | PSEB | GND TPS(BHATINDA) | State Sector | Punjab | NR | Steam | 2 | 110 | 1975-09-19 | 41.789 | COAL | N | N | N | Y |  |  | IDENTIFIED FOR RETIREMENT
31 | PSEB | GND TPS(BHATINDA) | State Sector | Punjab | NR | Steam | 3 | 110 | 1978-03-29 | 39.263 | COAL | N | N | N |  |  | 31/12/2017 | TO BE PHASED OUT
32 | PSEB | GND TPS(BHATINDA) | State Sector | Punjab | NR | Steam | 4 | 110 | 1979-01-31 | 38.4192 | COAL | N | N | N |  |  | 31/12/2017 | TO BE PHASED OUT
33 | PSEB | ROPAR TPS | State Sector | Punjab | NR | Steam | 1 | 210 | 1984-09-26 | 32.7616 | COAL | N | N | Y | Y |  |  | IDENTIFIED FOR RETIREMENT
34 | PSEB | ROPAR TPS | State Sector | Punjab | NR | Steam | 2 | 210 | 1985-03-30 | 32.2548 | COAL | N | N | Y | Y |  |  | IDENTIFIED FOR RETIREMENT
35 | PSEB | ROPAR TPS | State Sector | Punjab | NR | Steam | 3 | 210 | 1988-03-31 | 29.2493 | COAL | N | N | Y | Y |  |  | IDENTIFIED FOR RETIREMENT
36 | PSEB | ROPAR TPS | State Sector | Punjab | NR | Steam | 4 | 210 | 1989-01-29 | 28.4164 | COAL | N | N | Y | Y |  |  | IDENTIFIED FOR RETIREMENT
37 | PSEB | ROPAR TPS | State Sector | Punjab | NR | Steam | 5 | 210 | 1992-03-29 | 25.2521 | COAL | N | N | N |  |  | 31/12/2022 | TO BE PHASED OUT
38 | PSEB | ROPAR TPS | State Sector | Punjab | NR | Steam | 6 | 210 | 1993-03-30 | 24.2493 | COAL | N | N | Y |  |  | 31/12/2022 | TO BE PHASED OUT
39 | Talwandi Sabo Power Limited | TALWANDI SABO TPP | Private Sector | Punjab | NR | Steam | 1 | 660 | 2014-06-17 | 3.0192 | COAL | N | N | N |  | 25/06/2022 |  | FGD POSSIBLE
40 | Talwandi Sabo Power Limited | TALWANDI SABO TPP | Private Sector | Punjab | NR | Steam | 2 | 660 | 2015-10-25 | 1.663 | COAL | N | N | N |  | 25/08/2022 |  | FGD POSSIBLE
41 | Talwandi Sabo Power Limited | TALWANDI SABO TPP | Private Sector | Punjab | NR | Steam | 3 | 660 | 2016-03-29 | 1.2356 | COAL | N | N | N |  | 25/10/2022 |  | FGD POSSIBLE
42 | Adani Power Ltd. | KAWAI TPS | Private Sector | Rajasthan | NR | Steam | 1 | 660 | 2013-05-28 | 4.074 | COAL | N | N | N |  | 31/03/2022 |  | FGD POSSIBLE
43 | Adani Power Ltd. | KAWAI TPS | Private Sector | Rajasthan | NR | Steam | 2 | 660 | 2013-12-24 | 3.4986 | COAL | N | N | N |  | 30/06/2022 |  | FGD POSSIBLE
44 | JSW Rajwest Power Ltd | JALIPA KAPURDI TPP | Private Sector | Rajasthan | NR | Steam | 1 | 135 | 2009-10-16 | 7.6904 | Lignite | N | Y | Y |  | 31/03/2023 |  | ESP UPGRADATION/ CFBC BOILER
45 | JSW Rajwest Power Ltd | JALIPA KAPURDI TPP | Private Sector | Rajasthan | NR | Steam | 2 | 135 | 2010-07-08 | 6.9644 | Lignite | N | Y | Y |  | 31/03/2023 |  | ESP UPGRADATION/ CFBC BOILER
46 | JSW Rajwest Power Ltd | JALIPA KAPURDI TPP | Private Sector | Rajasthan | NR | Steam | 3 | 135 | 2011-11-02 | 5.6438 | Lignite | N | Y | Y |  | 30/06/2022 |  | ESP UPGRADATION/ CFBC BOILER
47 | JSW Rajwest Power Ltd | JALIPA KAPURDI TPP | Private Sector | Rajasthan | NR | Steam | 4 | 135 | 2011-11-23 | 5.5863 | Lignite | N | Y | Y |  | 30/06/2022 |  | ESP UPGRADATION/ CFBC BOILER
48 | JSW Rajwest Power Ltd | JALIPA KAPURDI TPP | Private Sector | Rajasthan | NR | Steam | 5 | 135 | 2013-02-05 | 4.3808 | Lignite | N | Y | Y |  | 31/03/2022 |  | ESP UPGRADATION/ CFBC BOILER
49 | JSW Rajwest Power Ltd | JALIPA KAPURDI TPP | Private Sector | Rajasthan | NR | Steam | 6 | 135 | 2013-03-03 | 4.3096 | Lignite | N | Y | Y |  | 30/09/2021 |  | ESP UPGRADATION/ CFBC BOILER
50 | JSW Rajwest Power Ltd | JALIPA KAPURDI TPP | Private Sector | Rajasthan | NR | Steam | 7 | 135 | 2013-03-16 | 4.274 | Lignite | N | Y | Y |  | 30/09/2021 |  | ESP UPGRADATION/ CFBC BOILER
51 | JSW Rajwest Power Ltd | JALIPA KAPURDI TPP | Private Sector | Rajasthan | NR | Steam | 8 | 135 | 2013-02-28 | 4.3178 | Lignite | N | Y | Y |  | 31/03/2022 |  | ESP UPGRADATION/ CFBC BOILER
52 | NEYVELI LIGNITE | BARSINGSAR LIGNITE | Central Sector | Rajasthan | NR | Steam | 1 | 125 | 2010-06-28 | 6.9918 | Lignite | N | Y | Y |  | 31/03/2019 |  | ESP UPGRADATION/ CFBC BOILER
53 | NEYVELI LIGNITE | BARSINGSAR LIGNITE | Central Sector | Rajasthan | NR | Steam | 2 | 125 | 2011-01-25 | 6.4137 | Lignite | N | Y | Y |  | 31/03/2019 |  | ESP UPGRADATION/ CFBC BOILER
54 | RRVUNL | CHHABRA TPP | State Sector | Rajasthan | NR | Steam | 1 | 250 | 2009-10-30 | 7.6521 | COAL | N | N | Y |  | 31/03/2022 |  | FGD POSSIBLE
55 | RRVUNL | CHHABRA TPP | State Sector | Rajasthan | NR | Steam | 2 | 250 | 2010-05-04 | 7.1425 | COAL | N | N | Y |  | 31/03/2022 |  | FGD POSSIBLE
56 | RRVUNL | CHHABRA TPP | State Sector | Rajasthan | NR | Steam | 3 | 250 | 2013-09-14 | 3.7753 | COAL | N | N | Y |  | 31/03/2022 |  | FGD POSSIBLE
57 | RRVUNL | CHHABRA TPP | State Sector | Rajasthan | NR | Steam | 4 | 250 | 2014-06-30 | 2.9836 | COAL | N | N | Y |  | 31/12/2021 |  | FGD POSSIBLE
58 | RRVUNL | CHHABRA TPP | State Sector | Rajasthan | NR | Steam | 5 | 660 | 2017-04-04 | 0.21918 | COAL | [6 empty] | FGD POSSIBLE
59 | RRVUNL | GIRAL TPS | State Sector | Rajasthan | NR | Steam | 1 | 125 | 2007-02-28 | 10.3233 | Lignite | N | Y | Y |  | under closure |  | CFBC BOILER
60 | RRVUNL | GIRAL TPS | State Sector | Rajasthan | NR | Steam | 2 | 125 | 2010-03-31 | 7.2356 | Lignite | N | Y | Y |  | under closure |  | CFBC BOILER
61 | RRVUNL | KALISINDH TPS | State Sector | Rajasthan | NR | Steam | 1 | 600 | 2014-05-02 | 3.1452 | COAL | N | N | N |  | 30/09/2021 |  | FGD POSSIBLE
62 | RRVUNL | KALISINDH TPS | State Sector | Rajasthan | NR | Steam | 2 | 600 | 2015-06-06 | 2.0493 | COAL | N | N | N |  | 30/09/2021 |  | FGD POSSIBLE
63 | RRVUNL | KOTA TPS | State Sector | Rajasthan | NR | Steam | 1 | 110 | 1983-01-17 | 34.4548 | COAL | N | N | Y |  |  | 31/12/2020 | TO BE PHASED OUT
64 | RRVUNL | KOTA TPS | State Sector | Rajasthan | NR | Steam | 2 | 110 | 1983-07-13 | 33.9699 | COAL | N | N | Y |  |  | 31/12/2020 | TO BE PHASED OUT
65 | RRVUNL | KOTA TPS | State Sector | Rajasthan | NR | Steam | 3 | 210 | 1988-09-25 | 28.7616 | COAL | N | N | Y |  |  | 31/12/2020 | TO BE PHASED OUT
66 | RRVUNL | KOTA TPS | State Sector | Rajasthan | NR | Steam | 4 | 210 | 1989-05-01 | 28.1644 | COAL | N | N | Y |  |  | 31/12/2020 | TO BE PHASED OUT
67 | RRVUNL | KOTA TPS | State Sector | Rajasthan | NR | Steam | 5 | 210 | 1994-03-26 | 23.2603 | COAL | N | N | Y |  |  | 31/12/2017 | TO BE PHASED OUT
68 | RRVUNL | KOTA TPS | State Sector | Rajasthan | NR | Steam | 7 | 195 | 2009-08-30 | 7.8192 | COAL | N | N | N |  | 30/06/2022 |  | FGD POSSIBLE
69 | RRVUNL | SURATGARH TPS | State Sector | Rajasthan | NR | Steam | 1 | 250 | 1998-05-10 | 19.1342 | COAL | N | N | N |  | 31/03/2023 |  | FGD POSSIBLE
70 | RRVUNL | SURATGARH TPS | State Sector | Rajasthan | NR | Steam | 2 | 250 | 2000-03-28 | 17.2493 | COAL | N | N | N |  | 30/06/2023 |  | FGD POSSIBLE
71 | RRVUNL | SURATGARH TPS | State Sector | Rajasthan | NR | Steam | 3 | 250 | 2001-10-29 | 15.6603 | COAL | N | N | N |  | 30/06/2023 |  | FGD POSSIBLE
72 | RRVUNL | SURATGARH TPS | State Sector | Rajasthan | NR | Steam | 4 | 250 | 2002-03-25 | 15.2575 | COAL | N | N | N |  | 31/03/2023 |  | FGD POSSIBLE
73 | RRVUNL | SURATGARH TPS | State Sector | Rajasthan | NR | Steam | 5 | 250 | 2003-06-30 | 13.9918 | COAL | N | N | N |  | 31/12/2022 |  | FGD POSSIBLE
74 | RRVUNL | SURATGARH TPS | State Sector | Rajasthan | NR | Steam | 6 | 250 | 2009-08-29 | 7.8219 | COAL | N | N | Y |  | 31/03/2023 |  | FGD POSSIBLE
75 | Bajaj Power Co | BARKHERA TPS | Private Sector | Uttar Pardesh | NR | Steam | 1 | 45 | 2011-11-06 | 5.6329 | COAL | N | Y | Y |  | 30/09/2021 |  | ESP UPGRADATION/ CFBC BOILER
76 | Bajaj Power Co | BARKHERA TPS | Private Sector | Uttar Pardesh | NR | Steam | 2 | 45 | 2012-01-28 | 5.4055 | COAL | N | Y | Y |  | 31/03/2021 |  | ESP UPGRADATION/ CFBC BOILER
77 | Bajaj Power Co | KHAMBARKHERA TPS | Private Sector | Uttar Pardesh | NR | Steam | 1 | 45 | 2011-10-17 | 5.6877 | COAL | N | Y | Y |  | 30/09/2021 |  | ESP UPGRADATION/ CFBC BOILER
78 | Bajaj Power Co | KHAMBARKHERA TPS | Private Sector | Uttar Pardesh | NR | Steam | 2 | 45 | 2011-11-28 | 5.5726 | COAL | N | Y | Y |  | 30/09/2021 |  | ESP UPGRADATION/ CFBC BOILER
79 | Bajaj Power Co | KUNDARKI TPS | Private Sector | Uttar Pardesh | NR | Steam | 1 | 45 | 2012-01-10 | 5.4548 | COAL | N | Y | Y |  | 30/09/2021 |  | ESP UPGRADATION/ CFBC BOILER
80 | Bajaj Power Co | KUNDARKI TPS | Private Sector | Uttar Pardesh | NR | Steam | 2 | 45 | 2012-02-29 | 5.3178 | COAL | N | Y | Y |  | 31/03/2021 |  | ESP UPGRADATION/ CFBC BOILER
81 | Bajaj Power Co | MAQSOODPUR TPS | Private Sector | Uttar Pardesh | NR | Steam | 1 | 45 | 2011-11-03 | 5.6411 | COAL | N | Y | Y |  | 30/09/2021 |  | ESP UPGRADATION/ CFBC BOILER
82 | Bajaj Power Co | MAQSOODPUR TPS | Private Sector | Uttar Pardesh | NR | Steam | 2 | 45 | 2012-01-21 | 5.4247 | COAL | N | Y | Y |  | 31/03/2021 |  | ESP UPGRADATION/ CFBC BOILER
83 | Bajaj Power Co | UTRAULA TPS | Private Sector | Uttar Pardesh | NR | Steam | 1 | 45 | 2012-02-21 | 5.3397 | COAL | N | Y | Y |  | 30/09/2021 |  | ESP UPGRADATION/ CFBC BOILER
84 | Bajaj Power Co | UTRAULA TPS | Private Sector | Uttar Pardesh | NR | Steam | 2 | 45 | 2012-03-19 | 5.2658 | COAL | N | Y | Y |  | 31/03/2021 |  | ESP UPGRADATION/ CFBC BOILER
85 | Lalitpur Power Gen. Co | LALITPUR TPS | Private Sector | Uttar Pardesh | NR | Steam | 2 | 660 | 2016-01-08 | 1.4575 | COAL | N | N | N |  | 30/09/2020 |  | FGD POSSIBLE
86 | Lalitpur Power Gen. Co | LALITPUR TPS | Private Sector | Uttar Pardesh | NR | Steam | 3 | 660 | 2016-04-01 | 1.2274 | COAL | N | N | N |  | 31/03/2020 |  | FGD POSSIBLE
87 | Lalitpur Power Gen. Co. | LALITPUR TPS | Private Sector | Uttar Pardesh | NR | Steam | 1 | 660 | 2016-03-26 | 1.2438 | COAL | N | N | N |  | 30/06/2020 |  | FGD POSSIBLE
88 | Lanko Anpara Pow Ltd | ANPARA C TPS | Private Sector | Uttar Pardesh | NR | Steam | 1 | 600 | 2011-10-12 | 5.7014 | COAL | N | N | N |  | 31/03/2023 |  | FGD POSSIBLE
89 | Lanko Anpara Pow Ltd | ANPARA C TPS | Private Sector | Uttar Pardesh | NR | Steam | 2 | 600 | 2012-01-18 | 5.4329 | COAL | N | N | N |  | 31/03/2023 |  | FGD POSSIBLE
90 | NTPC | DADRI (NCTPP) | Central Sector | Uttar Pardesh | NR | Steam | 1 | 210 | 1991-12-21 | 25.5233 | COAL | N | N | N |  | 31/12/2023 |  | FGD POSSIBLE
91 | NTPC | DADRI (NCTPP) | Central Sector | Uttar Pardesh | NR | Steam | 2 | 210 | 1992-12-18 | 24.5288 | COAL | N | N | N |  | 31/12/2023 |  | FGD POSSIBLE
92 | NTPC | DADRI (NCTPP) | Central Sector | Uttar Pardesh | NR | Steam | 3 | 210 | 1993-03-23 | 24.2685 | COAL | N | N | N |  | 31/12/2023 |  | FGD POSSIBLE
93 | NTPC | DADRI (NCTPP) | Central Sector | Uttar Pardesh | NR | Steam | 4 | 210 | 1994-03-24 | 23.2658 | COAL | N | N | N |  | 31/12/2023 |  | FGD POSSIBLE
94 | NTPC | DADRI (NCTPP) | Central Sector | Uttar Pardesh | NR | Steam | 5 | 490 | 2010-01-25 | 7.4137 | COAL | N | N | N |  | 31/03/2023 |  | FGD POSSIBLE
95 | NTPC | DADRI (NCTPP) | Central Sector | Uttar Pardesh | NR | Steam | 6 | 490 | 2010-07-16 | 6.9425 | COAL | N | N | N |  | 31/03/2023 |  | FGD POSSIBLE
96 | NTPC | RIHAND STPS | Central Sector | Uttar Pardesh | NR | Steam | 1 | 500 | 1988-03-31 | 29.2493 | COAL | N | N | Y |  | 31/12/2023 |  | FGD POSSIBLE
97 | NTPC | RIHAND STPS | Central Sector | Uttar Pardesh | NR | Steam | 2 | 500 | 1989-07-05 | 27.9863 | COAL | N | N | Y |  | 31/12/2023 |  | FGD POSSIBLE
98 | NTPC | RIHAND STPS | Central Sector | Uttar Pardesh | NR | Steam | 3 | 500 | 2005-01-31 | 12.4 | COAL | N | N | Y |  | 31/03/2023 |  | FGD POSSIBLE
99 | NTPC | RIHAND STPS | Central Sector | Uttar Pardesh | NR | Steam | 4 | 500 | 2005-09-24 | 11.7534 | COAL | N | N | Y |  | 31/03/2023 |  | FGD POSSIBLE
100 | NTPC | RIHAND STPS | Central Sector | Uttar Pardesh | NR | Steam | 5 | 500 | 2012-05-25 | 5.0822 | COAL | N | N | N |  | 31/03/2023 |  | FGD POSSIBLE
101 | NTPC | RIHAND STPS | Central Sector | Uttar Pardesh | NR | Steam | 6 | 500 | 2013-10-17 | 3.6849 | COAL | N | N | N |  | 31/03/2023 |  | FGD POSSIBLE
102 | NTPC | SINGRAULI STPS | Central Sector | Uttar Pardesh | NR | Steam | 1 | 200 | 1982-02-14 | 35.3781 | COAL | N | N | Y |  | 31/12/2023 |  | FGD POSSIBLE
103 | NTPC | SINGRAULI STPS | Central Sector | Uttar Pardesh | NR | Steam | 2 | 200 | 1982-11-25 | 34.6 | COAL | N | N | Y |  | 31/12/2023 |  | FGD POSSIBLE
104 | NTPC | SINGRAULI STPS | Central Sector | Uttar Pardesh | NR | Steam | 3 | 200 | 1983-03-28 | 34.263 | COAL | N | N | Y |  | 31/12/2023 |  | FGD POSSIBLE
105 | NTPC | SINGRAULI STPS | Central Sector | Uttar Pardesh | NR | Steam | 4 | 200 | 1983-11-02 | 33.663 | COAL | N | N | Y |  | 31/12/2023 |  | FGD POSSIBLE
106 | NTPC | SINGRAULI STPS | Central Sector | Uttar Pardesh | NR | Steam | 5 | 200 | 1984-02-26 | 33.3452 | COAL | N | N | Y |  | 31/12/2023 |  | FGD POSSIBLE
107 | NTPC | SINGRAULI STPS | Central Sector | Uttar Pardesh | NR | Steam | 6 | 500 | 1986-12-23 | 30.5205 | COAL | N | N | Y |  | 31/12/2023 |  | FGD POSSIBLE
108 | NTPC | SINGRAULI STPS | Central Sector | Uttar Pardesh | NR | Steam | 7 | 500 | 1987-11-24 | 29.6 | COAL | N | N | Y |  | 31/12/2023 |  | FGD POSSIBLE
109 | NTPC | TANDA TPS | Central Sector | Uttar Pardesh | NR | Steam | 1 | 110 | 1988-03-21 | 29.2767 | COAL | N | N | Y |  |  | 31/12/2021 | TO BE PHASED OUT
110 | NTPC | TANDA TPS | Central Sector | Uttar Pardesh | NR | Steam | 2 | 110 | 1989-03-11 | 28.3041 | COAL | N | N | Y |  |  | 31/12/2021 | TO BE PHASED OUT
111 | NTPC | TANDA TPS | Central Sector | Uttar Pardesh | NR | Steam | 3 | 110 | 1990-03-28 | 27.2575 | COAL | N | N | Y |  |  | 31/12/2021 | TO BE PHASED OUT
112 | NTPC | TANDA TPS | Central Sector | Uttar Pardesh | NR | Steam | 4 | 110 | 1998-02-20 | 19.3507 | COAL | N | N | Y |  |  | 31/12/2021 | TO BE PHASED OUT
113 | NTPC | UNCHAHAR TPS | Central Sector | Uttar Pardesh | NR | Steam | 1 | 210 | 1988-11-21 | 28.6055 | COAL | N | N | Y |  | 31/12/2023 |  | FGD POSSIBLE
114 | NTPC | UNCHAHAR TPS | Central Sector | Uttar Pardesh | NR | Steam | 2 | 210 | 1989-03-22 | 28.274 | COAL | N | N | Y |  | 31/12/2023 |  | FGD POSSIBLE
115 | NTPC | UNCHAHAR TPS | Central Sector | Uttar Pardesh | NR | Steam | 3 | 210 | 1999-01-27 | 18.4164 | COAL | N | N | Y |  | 31/12/2023 |  | FGD POSSIBLE
116 | NTPC | UNCHAHAR TPS | Central Sector | Uttar Pardesh | NR | Steam | 4 | 210 | 1999-10-22 | 17.6822 | COAL | N | N | Y |  | 31/12/2023 |  | FGD POSSIBLE
117 | NTPC | UNCHAHAR TPS | Central Sector | Uttar Pardesh | NR | Steam | 5 | 210 | 2006-09-28 | 10.7425 | COAL | N | N | Y |  | 31/03/2023 |  | FGD POSSIBLE
118 | NTPC | UNCHAHAR TPS | Central Sector | Uttar Pardesh | NR | Steam | 6 | 500 | 2017-03-31 | 0.23014 | COAL | [6 empty] | FGD POSSIBLE
119 | Prayagraj Power Generation Company LTD. | PRAYAGRAJ TPP | Private Sector | Uttar Pardesh | NR | Steam | 1 | 660 | 2016-12-25 | 0.49315 | COAL | N | N | N |  | 31/12/2020 |  | FGD POSSIBLE
120 | Prayagraj Power Generation Company LTD. | PRAYAGRAJ TPP | Private Sector | Uttar Pardesh | NR | Steam | 2 | 660 | 2015-09-06 | 1.7973 | COAL | N | N | N |  | 31/03/2021 |  | FGD POSSIBLE
121 | Prayagraj Power Generation Company LTD. | PRAYAGRAJ TPP | Private Sector | Uttar Pardesh | NR | Steam | 3 | 660 | 2017-05-22 | 0.087671 | COAL | [6 empty] | FGD POSSIBLE
122 | Rosa Power Supply Co | ROSA TPP Ph-I | Private Sector | Uttar Pardesh | NR | Steam | 1 | 300 | 2010-02-10 | 7.3699 | COAL | N | N | Y |  | 30/06/2023 |  | FGD POSSIBLE
123 | Rosa Power Supply Co | ROSA TPP Ph-I | Private Sector | Uttar Pardesh | NR | Steam | 2 | 300 | 2010-06-26 | 6.9973 | COAL | N | N | Y |  | 31/03/2023 |  | FGD POSSIBLE
124 | Rosa Power Supply Co | ROSA TPP Ph-I | Private Sector | Uttar Pardesh | NR | Steam | 3 | 300 | 2011-12-28 | 5.4904 | COAL | N | N | N |  | 31/03/2023 |  | FGD POSSIBLE
125 | Rosa Power Supply Co | ROSA TPP Ph-I | Private Sector | Uttar Pardesh | NR | Steam | 4 | 300 | 2012-03-28 | 5.2411 | COAL | N | N | N |  | 31/12/2022 |  | FGD POSSIBLE
126 | UPRVUNL | ANPARA TPS | State Sector | Uttar Pardesh | NR | Steam | 1 | 210 | 1986-03-24 | 31.2712 | COAL | N | N | Y |  | 31/03/2023 |  | FGD POSSIBLE
127 | UPRVUNL | ANPARA TPS | State Sector | Uttar Pardesh | NR | Steam | 2 | 210 | 1987-02-28 | 30.337 | COAL | N | N | Y |  | 30/06/2023 |  | FGD POSSIBLE
128 | UPRVUNL | ANPARA TPS | State Sector | Uttar Pardesh | NR | Steam | 3 | 210 | 1988-03-12 | 29.3014 | COAL | N | N | Y |  | 30/06/2023 |  | FGD POSSIBLE
129 | UPRVUNL | ANPARA TPS | State Sector | Uttar Pardesh | NR | Steam | 4 | 500 | 1993-07-19 | 23.9452 | COAL | N | N | Y |  | 31/03/2022 |  | FGD POSSIBLE
130 | UPRVUNL | ANPARA TPS | State Sector | Uttar Pardesh | NR | Steam | 5 | 500 | 1994-07-04 | 22.9863 | COAL | N | N | Y |  | 31/03/2022 |  | FGD POSSIBLE
131 | UPRVUNL | ANPARA TPS | State Sector | Uttar Pardesh | NR | Steam | 6 | 500 | 2015-06-08 | 2.0438 | COAL | N | N | N |  | 30/06/2021 |  | FGD POSSIBLE
132 | UPRVUNL | ANPARA TPS | State Sector | Uttar Pardesh | NR | Steam | 7 | 500 | 2016-03-06 | 1.2986 | COAL | N | N | Y |  | 31/03/2020 |  | FGD POSSIBLE
133 | UPRVUNL | HARDUAGANJ TPS | State Sector | Uttar Pardesh | NR | Steam | 5 | 60 | 1977-03-21 | 40.2849 | COAL | N | N | N | Y |  |  | RETIRED
134 | UPRVUNL | HARDUAGANJ TPS | State Sector | Uttar Pardesh | NR | Steam | 7 | 105 | 1978-03-31 | 39.2575 | COAL | N | N | N |  |  | 31/12/2022 | TO BE PHASED OUT
135 | UPRVUNL | HARDUAGANJ TPS | State Sector | Uttar Pardesh | NR | Steam | 8 | 250 | 2011-09-27 | 5.7425 | COAL | N | N | N |  | 30/06/2021 |  | FGD POSSIBLE
136 | UPRVUNL | HARDUAGANJ TPS | State Sector | Uttar Pardesh | NR | Steam | 9 | 250 | 2012-05-25 | 5.0822 | COAL | N | N | N |  | 31/03/2021 |  | FGD POSSIBLE
137 | UPRVUNL | OBRA TPS | State Sector | Uttar Pardesh | NR | Steam | 1 | 40 | 1967-08-15 | 49.8904 | COAL | N | N | Y | Y |  |  | RETIRED
138 | UPRVUNL | OBRA TPS | State Sector | Uttar Pardesh | NR | Steam | 2 | 50 | 1968-02-12 | 49.3945 | COAL | N | N | Y | Y |  |  | RETIRED
139 | UPRVUNL | OBRA TPS | State Sector | Uttar Pardesh | NR | Steam | 7 | 94 | 1974-12-14 | 42.5534 | COAL | N | N | Y |  |  | 31/12/2020 | TO BE PHASED OUT
140 | UPRVUNL | OBRA TPS | State Sector | Uttar Pardesh | NR | Steam | 8 | 94 | 1975-09-15 | 41.8 | COAL | N | N | Y | Y |  |  | IDENTIFIED FOR RETIREMENT
141 | UPRVUNL | OBRA TPS | State Sector | Uttar Pardesh | NR | Steam | 9 | 200 | 1980-10-26 | 36.6822 | COAL | N | N | N |  | 31/03/2023 |  | FGD POSSIBLE
142 | UPRVUNL | OBRA TPS | State Sector | Uttar Pardesh | NR | Steam | 10 | 200 | 1979-01-14 | 38.4658 | COAL | N | N | Y |  | 31/03/2023 |  | FGD POSSIBLE
143 | UPRVUNL | OBRA TPS | State Sector | Uttar Pardesh | NR | Steam | 11 | 200 | 1977-12-31 | 39.5041 | COAL | N | N | Y |  | 31/03/2023 |  | FGD POSSIBLE
144 | UPRVUNL | OBRA TPS | State Sector | Uttar Pardesh | NR | Steam | 12 | 200 | 1981-03-28 | 36.263 | COAL | N | N | Y |  | 30/06/2023 |  | FGD POSSIBLE
145 | UPRVUNL | OBRA TPS | State Sector | Uttar Pardesh | NR | Steam | 13 | 200 | 1982-07-21 | 34.9479 | COAL | N | N | Y |  | 30/06/2023 |  | FGD POSSIBLE
146 | UPRVUNL | PANKI TPS | State Sector | Uttar Pardesh | NR | Steam | 3 | 105 | 1976-11-10 | 40.6438 | COAL | N | N | Y | Y |  |  | IDENTIFIED FOR RETIREMENT
147 | UPRVUNL | PANKI TPS | State Sector | Uttar Pardesh | NR | Steam | 4 | 105 | 1977-03-24 | 40.2767 | COAL | N | N | Y | Y |  |  | IDENTIFIED FOR RETIREMENT
148 | UPRVUNL | PARICHHA TPS | State Sector | Uttar Pardesh | NR | Steam | 1 | 110 | 1984-03-31 | 33.2521 | COAL | N | N | Y |  |  | 31/12/2022 | TO BE PHASED OUT
149 | UPRVUNL | PARICHHA TPS | State Sector | Uttar Pardesh | NR | Steam | 2 | 110 | 1985-02-25 | 32.3452 | COAL | N | N | Y |  |  | 31/12/2022 | TO BE PHASED OUT
150 | UPRVUNL | PARICHHA TPS | State Sector | Uttar Pardesh | NR | Steam | 3 | 210 | 2006-03-29 | 11.2438 | COAL | N | N | Y |  | 30/06/2022 |  | FGD POSSIBLE
151 | UPRVUNL | PARICHHA TPS | State Sector | Uttar Pardesh | NR | Steam | 4 | 210 | 2006-12-28 | 10.4932 | COAL | N | N | Y |  | 31/12/2021 |  | FGD POSSIBLE
152 | UPRVUNL | PARICHHA TPS | State Sector | Uttar Pardesh | NR | Steam | 5 | 250 | 2012-05-24 | 5.0849 | COAL | N | N | Y |  | 31/03/2022 |  | FGD POSSIBLE
153 | UPRVUNL | PARICHHA TPS | State Sector | Uttar Pardesh | NR | Steam | 6 | 250 | 2013-03-11 | 4.2877 | COAL | N | N | Y |  | 30/09/2021 |  | FGD POSSIBLE
[5 empty] | TOTAL CAPACITY |  |  | 42768 MW
(153 Units)

## Retirement
Sr. No. | Developer | Name of Project | Sector | State | Region | Prime Mover | Unit No | Total Capacity | DT-of COMMISSIONING | Age in years | Type of Fuel | Whether FGD Installed | Whether CFBC | Whether ESP retrofit required | Identified for retirement | Phasing Plan for Implementation | Phase out plan | Comments of GM Division
1 | IPGCL | RAJGHAT TPS | State Sector | Delhi | NR | Steam | 1 | 67.5 | 1989-03-10 | 28.3068 | COAL | N | N | Y | Y |  |  | IDENTIFIED FOR RETIREMENT
2 | IPGCL | RAJGHAT TPS | State Sector | Delhi | NR | Steam | 2 | 67.5 | 1990-02-20 | 27.3562 | COAL | N | N | Y | Y |  |  | IDENTIFIED FOR RETIREMENT
3 | NTPC | BADARPUR TPS | Central Sector | Delhi | NR | Steam | 1 | 95 | 1973-07-26 | 43.9397 | COAL | N | N | Y | Y |  | 31/07/2018 | IDENTIFIED FOR RETIREMENT
4 | NTPC | BADARPUR TPS | Central Sector | Delhi | NR | Steam | 2 | 95 | 1974-08-05 | 42.9123 | COAL | N | N | Y | Y |  | 31/07/2018 | IDENTIFIED FOR RETIREMENT
5 | NTPC | BADARPUR TPS | Central Sector | Delhi | NR | Steam | 3 | 95 | 1975-03-29 | 42.2658 | COAL | N | N | Y | Y |  | 31/07/2018 | IDENTIFIED FOR RETIREMENT
6 | PSEB | GND TPS(BHATINDA) | State Sector | Punjab | NR | Steam | 1 | 110 | 1974-09-22 | 42.7808 | COAL | N | N | N | Y |  |  | IDENTIFIED FOR RETIREMENT
7 | PSEB | GND TPS(BHATINDA) | State Sector | Punjab | NR | Steam | 2 | 110 | 1975-09-19 | 41.789 | COAL | N | N | N | Y |  |  | IDENTIFIED FOR RETIREMENT
8 | PSEB | ROPAR TPS | State Sector | Punjab | NR | Steam | 1 | 210 | 1984-09-26 | 32.7616 | COAL | N | N | Y | Y |  |  | IDENTIFIED FOR RETIREMENT
9 | PSEB | ROPAR TPS | State Sector | Punjab | NR | Steam | 2 | 210 | 1985-03-30 | 32.2548 | COAL | N | N | Y | Y |  |  | IDENTIFIED FOR RETIREMENT
10 | PSEB | ROPAR TPS | State Sector | Punjab | NR | Steam | 3 | 210 | 1988-03-31 | 29.2493 | COAL | N | N | Y | Y |  |  | IDENTIFIED FOR RETIREMENT
11 | PSEB | ROPAR TPS | State Sector | Punjab | NR | Steam | 4 | 210 | 1989-01-29 | 28.4164 | COAL | N | N | Y | Y |  |  | IDENTIFIED FOR RETIREMENT
12 | UPRVUNL | HARDUAGANJ TPS | State Sector | Uttar Pardesh | NR | Steam | 5 | 60 | 1977-03-21 | 40.2849 | COAL | N | N | N | Y |  |  | RETIRED
13 | UPRVUNL | OBRA TPS | State Sector | Uttar Pardesh | NR | Steam | 1 | 40 | 1967-08-15 | 49.8904 | COAL | N | N | Y | Y |  |  | RETIRED
14 | UPRVUNL | OBRA TPS | State Sector | Uttar Pardesh | NR | Steam | 2 | 50 | 1968-02-12 | 49.3945 | COAL | N | N | Y | Y |  |  | RETIRED
15 | UPRVUNL | OBRA TPS | State Sector | Uttar Pardesh | NR | Steam | 8 | 94 | 1975-09-15 | 41.8 | COAL | N | N | Y | Y |  |  | IDENTIFIED FOR RETIREMENT
16 | UPRVUNL | PANKI TPS | State Sector | Uttar Pardesh | NR | Steam | 3 | 105 | 1976-11-10 | 40.6438 | COAL | N | N | Y | Y |  |  | IDENTIFIED FOR RETIREMENT
17 | UPRVUNL | PANKI TPS | State Sector | Uttar Pardesh | NR | Steam | 4 | 105 | 1977-03-24 | 40.2767 | COAL | N | N | Y | Y |  |  | IDENTIFIED FOR RETIREMENT
[5 empty] | TOTAL CAPACITY |  |  | 1934 MW
(17 Units)

## CFBC
Sr. No. | Developer | Name of Project | Sector | State | Region | Prime Mover | Unit No | Total Capacity | DT-of COMMISSIONING | Age in years | Type of Fuel | Whether FGD Installed | Whether CFBC | Whether ESP retrofit required | Identified for retirement | Phasing Plan for Implementation | Phase out plan | Comments of GM Division
1 | JSW Rajwest Power Ltd | JALIPA KAPURDI TPP | Private Sector | Rajasthan | NR | Steam | 1 | 135 | 2009-10-16 | 7.6904 | Lignite | N | Y | Y |  | 31/03/2023 |  | ESP UPGRADATION/ CFBC BOILER
2 | JSW Rajwest Power Ltd | JALIPA KAPURDI TPP | Private Sector | Rajasthan | NR | Steam | 2 | 135 | 2010-07-08 | 6.9644 | Lignite | N | Y | Y |  | 31/03/2023 |  | ESP UPGRADATION/ CFBC BOILER
3 | JSW Rajwest Power Ltd | JALIPA KAPURDI TPP | Private Sector | Rajasthan | NR | Steam | 3 | 135 | 2011-11-02 | 5.6438 | Lignite | N | Y | Y |  | 30/06/2022 |  | ESP UPGRADATION/ CFBC BOILER
4 | JSW Rajwest Power Ltd | JALIPA KAPURDI TPP | Private Sector | Rajasthan | NR | Steam | 4 | 135 | 2011-11-23 | 5.5863 | Lignite | N | Y | Y |  | 30/06/2022 |  | ESP UPGRADATION/ CFBC BOILER
5 | JSW Rajwest Power Ltd | JALIPA KAPURDI TPP | Private Sector | Rajasthan | NR | Steam | 5 | 135 | 2013-02-05 | 4.3808 | Lignite | N | Y | Y |  | 31/03/2022 |  | ESP UPGRADATION/ CFBC BOILER
6 | JSW Rajwest Power Ltd | JALIPA KAPURDI TPP | Private Sector | Rajasthan | NR | Steam | 6 | 135 | 2013-03-03 | 4.3096 | Lignite | N | Y | Y |  | 30/09/2021 |  | ESP UPGRADATION/ CFBC BOILER
7 | JSW Rajwest Power Ltd | JALIPA KAPURDI TPP | Private Sector | Rajasthan | NR | Steam | 7 | 135 | 2013-03-16 | 4.274 | Lignite | N | Y | Y |  | 30/09/2021 |  | ESP UPGRADATION/ CFBC BOILER
8 | JSW Rajwest Power Ltd | JALIPA KAPURDI TPP | Private Sector | Rajasthan | NR | Steam | 8 | 135 | 2013-02-28 | 4.3178 | Lignite | N | Y | Y |  | 31/03/2022 |  | ESP UPGRADATION/ CFBC BOILER
9 | NEYVELI LIGNITE | BARSINGSAR LIGNITE | Central Sector | Rajasthan | NR | Steam | 1 | 125 | 2010-06-28 | 6.9918 | Lignite | N | Y | Y |  | 31/03/2019 |  | ESP UPGRADATION/ CFBC BOILER
10 | NEYVELI LIGNITE | BARSINGSAR LIGNITE | Central Sector | Rajasthan | NR | Steam | 2 | 125 | 2011-01-25 | 6.4137 | Lignite | N | Y | Y |  | 31/03/2019 |  | ESP UPGRADATION/ CFBC BOILER
11 | RRVUNL | GIRAL TPS | State Sector | Rajasthan | NR | Steam | 1 | 125 | 2007-02-28 | 10.3233 | Lignite | N | Y | Y |  | under closure |  | CFBC BOILER
12 | RRVUNL | GIRAL TPS | State Sector | Rajasthan | NR | Steam | 2 | 125 | 2010-03-31 | 7.2356 | Lignite | N | Y | Y |  | under closure |  | CFBC BOILER
13 | Bajaj Power Co | BARKHERA TPS | Private Sector | Uttar Pardesh | NR | Steam | 1 | 45 | 2011-11-06 | 5.6329 | COAL | N | Y | Y |  | 30/09/2021 |  | ESP UPGRADATION/ CFBC BOILER
14 | Bajaj Power Co | BARKHERA TPS | Private Sector | Uttar Pardesh | NR | Steam | 2 | 45 | 2012-01-28 | 5.4055 | COAL | N | Y | Y |  | 31/03/2021 |  | ESP UPGRADATION/ CFBC BOILER
15 | Bajaj Power Co | KHAMBARKHERA TPS | Private Sector | Uttar Pardesh | NR | Steam | 1 | 45 | 2011-10-17 | 5.6877 | COAL | N | Y | Y |  | 30/09/2021 |  | ESP UPGRADATION/ CFBC BOILER
16 | Bajaj Power Co | KHAMBARKHERA TPS | Private Sector | Uttar Pardesh | NR | Steam | 2 | 45 | 2011-11-28 | 5.5726 | COAL | N | Y | Y |  | 30/09/2021 |  | ESP UPGRADATION/ CFBC BOILER
17 | Bajaj Power Co | KUNDARKI TPS | Private Sector | Uttar Pardesh | NR | Steam | 1 | 45 | 2012-01-10 | 5.4548 | COAL | N | Y | Y |  | 30/09/2021 |  | ESP UPGRADATION/ CFBC BOILER
18 | Bajaj Power Co | KUNDARKI TPS | Private Sector | Uttar Pardesh | NR | Steam | 2 | 45 | 2012-02-29 | 5.3178 | COAL | N | Y | Y |  | 31/03/2021 |  | ESP UPGRADATION/ CFBC BOILER
19 | Bajaj Power Co | MAQSOODPUR TPS | Private Sector | Uttar Pardesh | NR | Steam | 1 | 45 | 2011-11-03 | 5.6411 | COAL | N | Y | Y |  | 30/09/2021 |  | ESP UPGRADATION/ CFBC BOILER
20 | Bajaj Power Co | MAQSOODPUR TPS | Private Sector | Uttar Pardesh | NR | Steam | 2 | 45 | 2012-01-21 | 5.4247 | COAL | N | Y | Y |  | 31/03/2021 |  | ESP UPGRADATION/ CFBC BOILER
21 | Bajaj Power Co | UTRAULA TPS | Private Sector | Uttar Pardesh | NR | Steam | 1 | 45 | 2012-02-21 | 5.3397 | COAL | N | Y | Y |  | 30/09/2021 |  | ESP UPGRADATION/ CFBC BOILER
22 | Bajaj Power Co | UTRAULA TPS | Private Sector | Uttar Pardesh | NR | Steam | 2 | 45 | 2012-03-19 | 5.2658 | COAL | N | Y | Y |  | 31/03/2021 |  | ESP UPGRADATION/ CFBC BOILER
[5 empty] | TOTAL CAPACITY |  |  | 2030 MW
(22Units)

## FGD Installed
Sr. No. | Developer | Name of Project | Sector | State | Region | Prime Mover | Unit No | Total Capacity | DT-of COMMISSIONING | Age in years | Type of Fuel | Whether FGD Installed | Whether CFBC | Whether ESP retrofit required | Identified for retirement | Phasing Plan for Implementation | Phase out plan | Comments of GM Division
1 | CHINA LIGHT POWER | MAHATMA GANDHI TPS | Private Sector | Haryana | NR | Steam | 1 | 660 | 2012-01-12 | 5.4493 | COAL | Y | N | N |  |  |  | FGD INSTALLED
2 | CHINA LIGHT POWER | MAHATMA GANDHI TPS | Private Sector | Haryana | NR | Steam | 2 | 660 | 2012-04-11 | 5.2027 | COAL | Y | N | N |  |  |  | FGD INSTALLED
[5 empty] | TOTAL CAPACITY |  |  | 1320 MW
(2Units)

## SOx Compliant (hidden)
NIL

## FGD Planned
Sr. No. | Developer | Name of Project | Sector | State | Region | Prime Mover | Unit No | Total Capacity | DT-of COMMISSIONING | Age in years | Type of Fuel | Whether FGD Installed | Whether CFBC | Whether ESP retrofit required | Identified for retirement | Phasing Plan for Implementation | Phase out plan | Comments of GM Division
1 | HGPCorpn | PANIPAT TPS | State Sector | Haryana | NR | Steam | 6 | 210 | 2001-03-31 | 16.2411 | COAL | N | N | N |  | 30/06/2023 |  | FGD POSSIBLE
2 | HGPCorpn | PANIPAT TPS | State Sector | Haryana | NR | Steam | 7 | 250 | 2004-09-28 | 12.7425 | COAL | N | N | Y |  | 30/06/2023 |  | FGD POSSIBLE
3 | HGPCorpn | PANIPAT TPS | State Sector | Haryana | NR | Steam | 8 | 250 | 2005-01-28 | 12.4082 | COAL | N | N | Y |  | 30/06/2023 |  | FGD POSSIBLE
4 | HGPCorpn | RAJIV GANDHI TPS | State Sector | Haryana | NR | Steam | 1 | 600 | 2010-03-31 | 7.2356 | COAL | N | N | Y |  | 30/06/2023 |  | FGD POSSIBLE
5 | HGPCorpn | RAJIV GANDHI TPS | State Sector | Haryana | NR | Steam | 2 | 600 | 2010-10-01 | 6.7315 | COAL | N | N | Y |  | 31/03/2023 |  | FGD POSSIBLE
6 | HGPCorpn | YAMUNA NAGAR TPS | State Sector | Haryana | NR | Steam | 1 | 300 | 2007-11-01 | 9.6493 | COAL | N | N | Y |  | 31/12/2024 |  | FGD POSSIBLE
7 | HGPCorpn | YAMUNA NAGAR TPS | State Sector | Haryana | NR | Steam | 2 | 300 | 2008-03-29 | 9.2411 | COAL | N | N | Y |  | 31/12/2024 |  | FGD POSSIBLE
8 | NTPC | INDIRA GANDHI STPP | Central Sector | Haryana | NR | Steam | 1 | 500 | 2010-10-31 | 6.6493 | COAL | N | N | Y |  | 30/09/2021 |  | FGD POSSIBLE
9 | NTPC | INDIRA GANDHI STPP | Central Sector | Haryana | NR | Steam | 2 | 500 | 2011-11-05 | 5.6356 | COAL | N | N | Y |  | 30/06/2021 |  | FGD POSSIBLE
10 | NTPC | INDIRA GANDHI STPP | Central Sector | Haryana | NR | Steam | 3 | 500 | 2012-11-07 | 4.6274 | COAL | N | N | Y |  | 30/06/2021 |  | FGD POSSIBLE
11 | GVK Power Ltd. | GOINDWAL SAHIB | Private Sector | Punjab | NR | Steam | 1 | 270 | 2016-02-14 | 1.3562 | COAL | N | N | N |  | 30/06/2020 |  | FGD POSSIBLE
12 | GVK Power Ltd. | GOINDWAL SAHIB | Private Sector | Punjab | NR | Steam | 2 | 270 | 2016-03-15 | 1.274 | COAL | N | N | N |  | 31/03/2020 |  | FGD POSSIBLE
13 | L&T Power Development LTD(Nabha) | Nabha TPP (Rajpura TPP) | Private Sector | Punjab | NR | Steam | 1 | 700 | 2014-01-24 | 3.4137 | COAL | N | N | N |  | 31/03/2023 |  | FGD POSSIBLE
14 | L&T Power Development LTD(Nabha) | Nabha TPP (Rajpura TPP) | Private Sector | Punjab | NR | Steam | 2 | 700 | 2014-07-06 | 2.9671 | COAL | N | N | N |  | 31/12/2021 |  | FGD POSSIBLE
15 | PSEB | GH TPS (LEH.MOH.) | State Sector | Punjab | NR | Steam | 1 | 210 | 1997-12-29 | 19.4959 | COAL | N | N | Y |  | 31/12/2022 |  | FGD POSSIBLE
16 | PSEB | GH TPS (LEH.MOH.) | State Sector | Punjab | NR | Steam | 2 | 210 | 1998-10-16 | 18.6986 | COAL | N | N | Y |  | 30/06/2022 |  | FGD POSSIBLE
17 | PSEB | GH TPS (LEH.MOH.) | State Sector | Punjab | NR | Steam | 3 | 250 | 2008-01-03 | 9.4767 | COAL | N | N | Y |  | 31/03/2023 |  | FGD POSSIBLE
18 | PSEB | GH TPS (LEH.MOH.) | State Sector | Punjab | NR | Steam | 4 | 250 | 2008-07-31 | 8.9014 | COAL | N | N | Y |  | 31/03/2023 |  | FGD POSSIBLE
19 | Talwandi Sabo Power Limited | TALWANDI SABO TPP | Private Sector | Punjab | NR | Steam | 1 | 660 | 2014-06-17 | 3.0192 | COAL | N | N | N |  | 25/06/2022 |  | FGD POSSIBLE
20 | Talwandi Sabo Power Limited | TALWANDI SABO TPP | Private Sector | Punjab | NR | Steam | 2 | 660 | 2015-10-25 | 1.663 | COAL | N | N | N |  | 25/08/2022 |  | FGD POSSIBLE
21 | Talwandi Sabo Power Limited | TALWANDI SABO TPP | Private Sector | Punjab | NR | Steam | 3 | 660 | 2016-03-29 | 1.2356 | COAL | N | N | N |  | 25/10/2022 |  | FGD POSSIBLE
22 | Adani Power Ltd. | KAWAI TPS | Private Sector | Rajasthan | NR | Steam | 1 | 660 | 2013-05-28 | 4.074 | COAL | N | N | N |  | 31/03/2022 |  | FGD POSSIBLE
23 | Adani Power Ltd. | KAWAI TPS | Private Sector | Rajasthan | NR | Steam | 2 | 660 | 2013-12-24 | 3.4986 | COAL | N | N | N |  | 30/06/2022 |  | FGD POSSIBLE
24 | RRVUNL | CHHABRA TPP | State Sector | Rajasthan | NR | Steam | 1 | 250 | 2009-10-30 | 7.6521 | COAL | N | N | Y |  | 31/03/2022 |  | FGD POSSIBLE
25 | RRVUNL | CHHABRA TPP | State Sector | Rajasthan | NR | Steam | 2 | 250 | 2010-05-04 | 7.1425 | COAL | N | N | Y |  | 31/03/2022 |  | FGD POSSIBLE
26 | RRVUNL | CHHABRA TPP | State Sector | Rajasthan | NR | Steam | 3 | 250 | 2013-09-14 | 3.7753 | COAL | N | N | Y |  | 31/03/2022 |  | FGD POSSIBLE
27 | RRVUNL | CHHABRA TPP | State Sector | Rajasthan | NR | Steam | 4 | 250 | 2014-06-30 | 2.9836 | COAL | N | N | Y |  | 31/12/2021 |  | FGD POSSIBLE
28 | RRVUNL | CHHABRA TPP | State Sector | Rajasthan | NR | Steam | 5 | 660 | 2017-04-04 | 0.21918 | COAL | [6 empty] | FGD POSSIBLE
29 | RRVUNL | KALISINDH TPS | State Sector | Rajasthan | NR | Steam | 1 | 600 | 2014-05-02 | 3.1452 | COAL | N | N | N |  | 30/09/2021 |  | FGD POSSIBLE
30 | RRVUNL | KALISINDH TPS | State Sector | Rajasthan | NR | Steam | 2 | 600 | 2015-06-06 | 2.0493 | COAL | N | N | N |  | 30/09/2021 |  | FGD POSSIBLE
31 | RRVUNL | KOTA TPS | State Sector | Rajasthan | NR | Steam | 7 | 195 | 2009-08-30 | 7.8192 | COAL | N | N | N |  | 30/06/2022 |  | FGD POSSIBLE
32 | RRVUNL | SURATGARH TPS | State Sector | Rajasthan | NR | Steam | 1 | 250 | 1998-05-10 | 19.1342 | COAL | N | N | N |  | 31/03/2023 |  | FGD POSSIBLE
33 | RRVUNL | SURATGARH TPS | State Sector | Rajasthan | NR | Steam | 2 | 250 | 2000-03-28 | 17.2493 | COAL | N | N | N |  | 30/06/2023 |  | FGD POSSIBLE
34 | RRVUNL | SURATGARH TPS | State Sector | Rajasthan | NR | Steam | 3 | 250 | 2001-10-29 | 15.6603 | COAL | N | N | N |  | 30/06/2023 |  | FGD POSSIBLE
35 | RRVUNL | SURATGARH TPS | State Sector | Rajasthan | NR | Steam | 4 | 250 | 2002-03-25 | 15.2575 | COAL | N | N | N |  | 31/03/2023 |  | FGD POSSIBLE
36 | RRVUNL | SURATGARH TPS | State Sector | Rajasthan | NR | Steam | 5 | 250 | 2003-06-30 | 13.9918 | COAL | N | N | N |  | 31/12/2022 |  | FGD POSSIBLE
37 | RRVUNL | SURATGARH TPS | State Sector | Rajasthan | NR | Steam | 6 | 250 | 2009-08-29 | 7.8219 | COAL | N | N | Y |  | 31/03/2023 |  | FGD POSSIBLE
38 | Lalitpur Power Gen. Co | LALITPUR TPS | Private Sector | Uttar Pardesh | NR | Steam | 2 | 660 | 2016-01-08 | 1.4575 | COAL | N | N | N |  | 30/09/2020 |  | FGD POSSIBLE
39 | Lalitpur Power Gen. Co | LALITPUR TPS | Private Sector | Uttar Pardesh | NR | Steam | 3 | 660 | 2016-04-01 | 1.2274 | COAL | N | N | N |  | 31/03/2020 |  | FGD POSSIBLE
40 | Lalitpur Power Gen. Co. | LALITPUR TPS | Private Sector | Uttar Pardesh | NR | Steam | 1 | 660 | 2016-03-26 | 1.2438 | COAL | N | N | N |  | 30/06/2020 |  | FGD POSSIBLE
41 | Lanko Anpara Pow Ltd | ANPARA C TPS | Private Sector | Uttar Pardesh | NR | Steam | 1 | 600 | 2011-10-12 | 5.7014 | COAL | N | N | N |  | 31/03/2023 |  | FGD POSSIBLE
42 | Lanko Anpara Pow Ltd | ANPARA C TPS | Private Sector | Uttar Pardesh | NR | Steam | 2 | 600 | 2012-01-18 | 5.4329 | COAL | N | N | N |  | 31/03/2023 |  | FGD POSSIBLE
43 | NTPC | DADRI (NCTPP) | Central Sector | Uttar Pardesh | NR | Steam | 1 | 210 | 1991-12-21 | 25.5233 | COAL | N | N | N |  | 31/12/2023 |  | FGD POSSIBLE
44 | NTPC | DADRI (NCTPP) | Central Sector | Uttar Pardesh | NR | Steam | 2 | 210 | 1992-12-18 | 24.5288 | COAL | N | N | N |  | 31/12/2023 |  | FGD POSSIBLE
45 | NTPC | DADRI (NCTPP) | Central Sector | Uttar Pardesh | NR | Steam | 3 | 210 | 1993-03-23 | 24.2685 | COAL | N | N | N |  | 31/12/2023 |  | FGD POSSIBLE
46 | NTPC | DADRI (NCTPP) | Central Sector | Uttar Pardesh | NR | Steam | 4 | 210 | 1994-03-24 | 23.2658 | COAL | N | N | N |  | 31/12/2023 |  | FGD POSSIBLE
47 | NTPC | DADRI (NCTPP) | Central Sector | Uttar Pardesh | NR | Steam | 5 | 490 | 2010-01-25 | 7.4137 | COAL | N | N | N |  | 31/03/2023 |  | FGD POSSIBLE
48 | NTPC | DADRI (NCTPP) | Central Sector | Uttar Pardesh | NR | Steam | 6 | 490 | 2010-07-16 | 6.9425 | COAL | N | N | N |  | 31/03/2023 |  | FGD POSSIBLE
49 | NTPC | RIHAND STPS | Central Sector | Uttar Pardesh | NR | Steam | 1 | 500 | 1988-03-31 | 29.2493 | COAL | N | N | Y |  | 31/12/2023 |  | FGD POSSIBLE
50 | NTPC | RIHAND STPS | Central Sector | Uttar Pardesh | NR | Steam | 2 | 500 | 1989-07-05 | 27.9863 | COAL | N | N | Y |  | 31/12/2023 |  | FGD POSSIBLE
51 | NTPC | RIHAND STPS | Central Sector | Uttar Pardesh | NR | Steam | 3 | 500 | 2005-01-31 | 12.4 | COAL | N | N | Y |  | 31/03/2023 |  | FGD POSSIBLE
52 | NTPC | RIHAND STPS | Central Sector | Uttar Pardesh | NR | Steam | 4 | 500 | 2005-09-24 | 11.7534 | COAL | N | N | Y |  | 31/03/2023 |  | FGD POSSIBLE
53 | NTPC | RIHAND STPS | Central Sector | Uttar Pardesh | NR | Steam | 5 | 500 | 2012-05-25 | 5.0822 | COAL | N | N | N |  | 31/03/2023 |  | FGD POSSIBLE
54 | NTPC | RIHAND STPS | Central Sector | Uttar Pardesh | NR | Steam | 6 | 500 | 2013-10-17 | 3.6849 | COAL | N | N | N |  | 31/03/2023 |  | FGD POSSIBLE
55 | NTPC | SINGRAULI STPS | Central Sector | Uttar Pardesh | NR | Steam | 1 | 200 | 1982-02-14 | 35.3781 | COAL | N | N | Y |  | 31/12/2023 |  | FGD POSSIBLE
56 | NTPC | SINGRAULI STPS | Central Sector | Uttar Pardesh | NR | Steam | 2 | 200 | 1982-11-25 | 34.6 | COAL | N | N | Y |  | 31/12/2023 |  | FGD POSSIBLE
57 | NTPC | SINGRAULI STPS | Central Sector | Uttar Pardesh | NR | Steam | 3 | 200 | 1983-03-28 | 34.263 | COAL | N | N | Y |  | 31/12/2023 |  | FGD POSSIBLE
58 | NTPC | SINGRAULI STPS | Central Sector | Uttar Pardesh | NR | Steam | 4 | 200 | 1983-11-02 | 33.663 | COAL | N | N | Y |  | 31/12/2023 |  | FGD POSSIBLE
59 | NTPC | SINGRAULI STPS | Central Sector | Uttar Pardesh | NR | Steam | 5 | 200 | 1984-02-26 | 33.3452 | COAL | N | N | Y |  | 31/12/2023 |  | FGD POSSIBLE
60 | NTPC | SINGRAULI STPS | Central Sector | Uttar Pardesh | NR | Steam | 6 | 500 | 1986-12-23 | 30.5205 | COAL | N | N | Y |  | 31/12/2023 |  | FGD POSSIBLE
61 | NTPC | SINGRAULI STPS | Central Sector | Uttar Pardesh | NR | Steam | 7 | 500 | 1987-11-24 | 29.6 | COAL | N | N | Y |  | 31/12/2023 |  | FGD POSSIBLE
62 | NTPC | UNCHAHAR TPS | Central Sector | Uttar Pardesh | NR | Steam | 1 | 210 | 1988-11-21 | 28.6055 | COAL | N | N | Y |  | 31/12/2023 |  | FGD POSSIBLE
63 | NTPC | UNCHAHAR TPS | Central Sector | Uttar Pardesh | NR | Steam | 2 | 210 | 1989-03-22 | 28.274 | COAL | N | N | Y |  | 31/12/2023 |  | FGD POSSIBLE
64 | NTPC | UNCHAHAR TPS | Central Sector | Uttar Pardesh | NR | Steam | 3 | 210 | 1999-01-27 | 18.4164 | COAL | N | N | Y |  | 31/12/2023 |  | FGD POSSIBLE
65 | NTPC | UNCHAHAR TPS | Central Sector | Uttar Pardesh | NR | Steam | 4 | 210 | 1999-10-22 | 17.6822 | COAL | N | N | Y |  | 31/12/2023 |  | FGD POSSIBLE
66 | NTPC | UNCHAHAR TPS | Central Sector | Uttar Pardesh | NR | Steam | 5 | 210 | 2006-09-28 | 10.7425 | COAL | N | N | Y |  | 31/03/2023 |  | FGD POSSIBLE
67 | NTPC | UNCHAHAR TPS | Central Sector | Uttar Pardesh | NR | Steam | 6 | 500 | 2017-03-31 | 0.23014 | COAL | [6 empty] | FGD POSSIBLE
68 | Prayagraj Power Generation Company LTD. | PRAYAGRAJ TPP | Private Sector | Uttar Pardesh | NR | Steam | 1 | 660 | 2016-12-25 | 0.49315 | COAL | N | N | N |  | 31/12/2020 |  | FGD POSSIBLE
69 | Prayagraj Power Generation Company LTD. | PRAYAGRAJ TPP | Private Sector | Uttar Pardesh | NR | Steam | 2 | 660 | 2015-09-06 | 1.7973 | COAL | N | N | N |  | 31/03/2021 |  | FGD POSSIBLE
70 | Prayagraj Power Generation Company LTD. | PRAYAGRAJ TPP | Private Sector | Uttar Pardesh | NR | Steam | 3 | 660 | 2017-05-22 | 0.087671 | COAL | [6 empty] | FGD POSSIBLE
71 | Rosa Power Supply Co | ROSA TPP Ph-I | Private Sector | Uttar Pardesh | NR | Steam | 1 | 300 | 2010-02-10 | 7.3699 | COAL | N | N | Y |  | 30/06/2023 |  | FGD POSSIBLE
72 | Rosa Power Supply Co | ROSA TPP Ph-I | Private Sector | Uttar Pardesh | NR | Steam | 2 | 300 | 2010-06-26 | 6.9973 | COAL | N | N | Y |  | 31/03/2023 |  | FGD POSSIBLE
73 | Rosa Power Supply Co | ROSA TPP Ph-I | Private Sector | Uttar Pardesh | NR | Steam | 3 | 300 | 2011-12-28 | 5.4904 | COAL | N | N | N |  | 31/03/2023 |  | FGD POSSIBLE
74 | Rosa Power Supply Co | ROSA TPP Ph-I | Private Sector | Uttar Pardesh | NR | Steam | 4 | 300 | 2012-03-28 | 5.2411 | COAL | N | N | N |  | 31/12/2022 |  | FGD POSSIBLE
75 | UPRVUNL | ANPARA TPS | State Sector | Uttar Pardesh | NR | Steam | 1 | 210 | 1986-03-24 | 31.2712 | COAL | N | N | Y |  | 31/03/2023 |  | FGD POSSIBLE
76 | UPRVUNL | ANPARA TPS | State Sector | Uttar Pardesh | NR | Steam | 2 | 210 | 1987-02-28 | 30.337 | COAL | N | N | Y |  | 30/06/2023 |  | FGD POSSIBLE
77 | UPRVUNL | ANPARA TPS | State Sector | Uttar Pardesh | NR | Steam | 3 | 210 | 1988-03-12 | 29.3014 | COAL | N | N | Y |  | 30/06/2023 |  | FGD POSSIBLE
78 | UPRVUNL | ANPARA TPS | State Sector | Uttar Pardesh | NR | Steam | 4 | 500 | 1993-07-19 | 23.9452 | COAL | N | N | Y |  | 31/03/2022 |  | FGD POSSIBLE
79 | UPRVUNL | ANPARA TPS | State Sector | Uttar Pardesh | NR | Steam | 5 | 500 | 1994-07-04 | 22.9863 | COAL | N | N | Y |  | 31/03/2022 |  | FGD POSSIBLE
80 | UPRVUNL | ANPARA TPS | State Sector | Uttar Pardesh | NR | Steam | 6 | 500 | 2015-06-08 | 2.0438 | COAL | N | N | N |  | 30/06/2021 |  | FGD POSSIBLE
81 | UPRVUNL | ANPARA TPS | State Sector | Uttar Pardesh | NR | Steam | 7 | 500 | 2016-03-06 | 1.2986 | COAL | N | N | Y |  | 31/03/2020 |  | FGD POSSIBLE
82 | UPRVUNL | HARDUAGANJ TPS | State Sector | Uttar Pardesh | NR | Steam | 8 | 250 | 2011-09-27 | 5.7425 | COAL | N | N | N |  | 30/06/2021 |  | FGD POSSIBLE
83 | UPRVUNL | HARDUAGANJ TPS | State Sector | Uttar Pardesh | NR | Steam | 9 | 250 | 2012-05-25 | 5.0822 | COAL | N | N | N |  | 31/03/2021 |  | FGD POSSIBLE
84 | UPRVUNL | OBRA TPS | State Sector | Uttar Pardesh | NR | Steam | 9 | 200 | 1980-10-26 | 36.6822 | COAL | N | N | N |  | 31/03/2023 |  | FGD POSSIBLE
85 | UPRVUNL | OBRA TPS | State Sector | Uttar Pardesh | NR | Steam | 10 | 200 | 1979-01-14 | 38.4658 | COAL | N | N | Y |  | 31/03/2023 |  | FGD POSSIBLE
86 | UPRVUNL | OBRA TPS | State Sector | Uttar Pardesh | NR | Steam | 11 | 200 | 1977-12-31 | 39.5041 | COAL | N | N | Y |  | 31/03/2023 |  | FGD POSSIBLE
87 | UPRVUNL | OBRA TPS | State Sector | Uttar Pardesh | NR | Steam | 12 | 200 | 1981-03-28 | 36.263 | COAL | N | N | Y |  | 30/06/2023 |  | FGD POSSIBLE
88 | UPRVUNL | OBRA TPS | State Sector | Uttar Pardesh | NR | Steam | 13 | 200 | 1982-07-21 | 34.9479 | COAL | N | N | Y |  | 30/06/2023 |  | FGD POSSIBLE
89 | UPRVUNL | PARICHHA TPS | State Sector | Uttar Pardesh | NR | Steam | 3 | 210 | 2006-03-29 | 11.2438 | COAL | N | N | Y |  | 30/06/2022 |  | FGD POSSIBLE
90 | UPRVUNL | PARICHHA TPS | State Sector | Uttar Pardesh | NR | Steam | 4 | 210 | 2006-12-28 | 10.4932 | COAL | N | N | Y |  | 31/12/2021 |  | FGD POSSIBLE
91 | UPRVUNL | PARICHHA TPS | State Sector | Uttar Pardesh | NR | Steam | 5 | 250 | 2012-05-24 | 5.0849 | COAL | N | N | Y |  | 31/03/2022 |  | FGD POSSIBLE
92 | UPRVUNL | PARICHHA TPS | State Sector | Uttar Pardesh | NR | Steam | 6 | 250 | 2013-03-11 | 4.2877 | COAL | N | N | Y |  | 30/09/2021 |  | FGD POSSIBLE
[5 empty] | TOTAL CAPACITY |  |  | 34505 MW
(92 Units)
YEAR-WISE PHASING PLAN
[9 empty] | YEAR | Capacity | Units
[9 empty] | 2019 | 0 | 0
[9 empty] | 2020 | 3680 | 7
[9 empty] | 2021 | 5770 | 13
[9 empty] | 2022 | 6675 | 17
[9 empty] | 2023 | 15960 | 50
[9 empty] | 2024 | 600 | 2
[9 empty] | NO PLAN | 1820 | 3
[9 empty] | Total | 34505 | 92

## FGD being explored (hidden)
NIL

## FGD not possible
Sr. No. | Developer | Name of Project | Sector | State | Region | Prime Mover | Unit No | Total Capacity | DT-of COMMISSIONING | Age in years | Type of Fuel | Whether FGD Installed | Whether CFBC | Whether ESP retrofit required | Identified for retirement | Phasing Plan for Implementation | Phase out plan | Comments of GM Division
1 | NTPC | BADARPUR TPS | Central Sector | Delhi | NR | Steam | 4 | 210 | 1978-12-02 | 38.5836 | COAL | N | N | N |  |  | 31/07/2018 | TO BE PHASED OUT
2 | NTPC | BADARPUR TPS | Central Sector | Delhi | NR | Steam | 5 | 210 | 1981-12-25 | 35.5178 | COAL | N | N | N |  |  | 31/07/2018 | TO BE PHASED OUT
3 | HGPCorpn | PANIPAT TPS | State Sector | Haryana | NR | Steam | 5 | 210 | 1989-03-28 | 28.2575 | COAL | N | N | N |  |  | 31/12/2018 | TO BE PHASED OUT
4 | PSEB | GND TPS(BHATINDA) | State Sector | Punjab | NR | Steam | 3 | 110 | 1978-03-29 | 39.263 | COAL | N | N | N |  |  | 31/12/2017 | TO BE PHASED OUT
5 | PSEB | GND TPS(BHATINDA) | State Sector | Punjab | NR | Steam | 4 | 110 | 1979-01-31 | 38.4192 | COAL | N | N | N |  |  | 31/12/2017 | TO BE PHASED OUT
6 | PSEB | ROPAR TPS | State Sector | Punjab | NR | Steam | 5 | 210 | 1992-03-29 | 25.2521 | COAL | N | N | N |  |  | 31/12/2022 | TO BE PHASED OUT
7 | PSEB | ROPAR TPS | State Sector | Punjab | NR | Steam | 6 | 210 | 1993-03-30 | 24.2493 | COAL | N | N | Y |  |  | 31/12/2022 | TO BE PHASED OUT
8 | RRVUNL | KOTA TPS | State Sector | Rajasthan | NR | Steam | 1 | 110 | 1983-01-17 | 34.4548 | COAL | N | N | Y |  |  | 31/12/2020 | TO BE PHASED OUT
9 | RRVUNL | KOTA TPS | State Sector | Rajasthan | NR | Steam | 2 | 110 | 1983-07-13 | 33.9699 | COAL | N | N | Y |  |  | 31/12/2020 | TO BE PHASED OUT
10 | RRVUNL | KOTA TPS | State Sector | Rajasthan | NR | Steam | 3 | 210 | 1988-09-25 | 28.7616 | COAL | N | N | Y |  |  | 31/12/2020 | TO BE PHASED OUT
11 | RRVUNL | KOTA TPS | State Sector | Rajasthan | NR | Steam | 4 | 210 | 1989-05-01 | 28.1644 | COAL | N | N | Y |  |  | 31/12/2020 | TO BE PHASED OUT
12 | RRVUNL | KOTA TPS | State Sector | Rajasthan | NR | Steam | 5 | 210 | 1994-03-26 | 23.2603 | COAL | N | N | Y |  |  | 31/12/2017 | TO BE PHASED OUT
13 | NTPC | TANDA TPS | Central Sector | Uttar Pardesh | NR | Steam | 1 | 110 | 1988-03-21 | 29.2767 | COAL | N | N | Y |  |  | 31/12/2021 | TO BE PHASED OUT
14 | NTPC | TANDA TPS | Central Sector | Uttar Pardesh | NR | Steam | 2 | 110 | 1989-03-11 | 28.3041 | COAL | N | N | Y |  |  | 31/12/2021 | TO BE PHASED OUT
15 | NTPC | TANDA TPS | Central Sector | Uttar Pardesh | NR | Steam | 3 | 110 | 1990-03-28 | 27.2575 | COAL | N | N | Y |  |  | 31/12/2021 | TO BE PHASED OUT
16 | NTPC | TANDA TPS | Central Sector | Uttar Pardesh | NR | Steam | 4 | 110 | 1998-02-20 | 19.3507 | COAL | N | N | Y |  |  | 31/12/2021 | TO BE PHASED OUT
17 | UPRVUNL | HARDUAGANJ TPS | State Sector | Uttar Pardesh | NR | Steam | 7 | 105 | 1978-03-31 | 39.2575 | COAL | N | N | N |  |  | 31/12/2022 | TO BE PHASED OUT
18 | UPRVUNL | OBRA TPS | State Sector | Uttar Pardesh | NR | Steam | 7 | 94 | 1974-12-14 | 42.5534 | COAL | N | N | Y |  |  | 31/12/2020 | TO BE PHASED OUT
19 | UPRVUNL | PARICHHA TPS | State Sector | Uttar Pardesh | NR | Steam | 1 | 110 | 1984-03-31 | 33.2521 | COAL | N | N | Y |  |  | 31/12/2022 | TO BE PHASED OUT
20 | UPRVUNL | PARICHHA TPS | State Sector | Uttar Pardesh | NR | Steam | 2 | 110 | 1985-02-25 | 32.3452 | COAL | N | N | Y |  |  | 31/12/2022 | TO BE PHASED OUT
[5 empty] | TOTAL CAPACITY |  |  | 2979 MW
(20 Units)

## ESP PHASING
Sr. No. | Developer | Name of Project | Sector | State | Region | Prime Mover | Unit No | Total Capacity | DT-of COMMISSIONING | Age in years | Type of Fuel | Whether FGD Installed | Whether CFBC | Whether ESP retrofit required | Whether ESP upgrade planned (Y/N) | Identified for retirement | Phasing Plan for Implementation | Phase out plan | Comments of GM Division
1 | JSW Rajwest Power Ltd | JALIPA KAPURDI TPP | Private Sector | Rajasthan | NR | Steam | 1 | 135 | 2009-10-16 | 7.6904 | Lignite | N | Y | Y | Y |  | 31/03/2023 |  | ESP UPGRADATION/ CFBC BOILER
2 | JSW Rajwest Power Ltd | JALIPA KAPURDI TPP | Private Sector | Rajasthan | NR | Steam | 2 | 135 | 2010-07-08 | 6.9644 | Lignite | N | Y | Y | Y |  | 31/03/2023 |  | ESP UPGRADATION/ CFBC BOILER
3 | JSW Rajwest Power Ltd | JALIPA KAPURDI TPP | Private Sector | Rajasthan | NR | Steam | 3 | 135 | 2011-11-02 | 5.6438 | Lignite | N | Y | Y | Y |  | 30/06/2022 |  | ESP UPGRADATION/ CFBC BOILER
4 | JSW Rajwest Power Ltd | JALIPA KAPURDI TPP | Private Sector | Rajasthan | NR | Steam | 4 | 135 | 2011-11-23 | 5.5863 | Lignite | N | Y | Y | Y |  | 30/06/2022 |  | ESP UPGRADATION/ CFBC BOILER
5 | JSW Rajwest Power Ltd | JALIPA KAPURDI TPP | Private Sector | Rajasthan | NR | Steam | 5 | 135 | 2013-02-05 | 4.3808 | Lignite | N | Y | Y | Y |  | 31/03/2022 |  | ESP UPGRADATION/ CFBC BOILER
6 | JSW Rajwest Power Ltd | JALIPA KAPURDI TPP | Private Sector | Rajasthan | NR | Steam | 6 | 135 | 2013-03-03 | 4.3096 | Lignite | N | Y | Y | Y |  | 30/09/2021 |  | ESP UPGRADATION/ CFBC BOILER
7 | JSW Rajwest Power Ltd | JALIPA KAPURDI TPP | Private Sector | Rajasthan | NR | Steam | 7 | 135 | 2013-03-16 | 4.274 | Lignite | N | Y | Y | Y |  | 30/09/2021 |  | ESP UPGRADATION/ CFBC BOILER
8 | JSW Rajwest Power Ltd | JALIPA KAPURDI TPP | Private Sector | Rajasthan | NR | Steam | 8 | 135 | 2013-02-28 | 4.3178 | Lignite | N | Y | Y | Y |  | 31/03/2022 |  | ESP UPGRADATION/ CFBC BOILER
9 | NEYVELI LIGNITE | BARSINGSAR LIGNITE | Central Sector | Rajasthan | NR | Steam | 1 | 125 | 2010-06-28 | 6.9918 | Lignite | N | Y | Y | Y |  | 31/03/2019 |  | ESP UPGRADATION/ CFBC BOILER
10 | NEYVELI LIGNITE | BARSINGSAR LIGNITE | Central Sector | Rajasthan | NR | Steam | 2 | 125 | 2011-01-25 | 6.4137 | Lignite | N | Y | Y | Y |  | 31/03/2019 |  | ESP UPGRADATION/ CFBC BOILER
11 | RRVUNL | GIRAL TPS | State Sector | Rajasthan | NR | Steam | 1 | 125 | 2007-02-28 | 10.3233 | Lignite | N | Y | Y |  |  | under closure |  | CFBC BOILER
12 | RRVUNL | GIRAL TPS | State Sector | Rajasthan | NR | Steam | 2 | 125 | 2010-03-31 | 7.2356 | Lignite | N | Y | Y |  |  | under closure |  | CFBC BOILER
13 | Bajaj Power Co | BARKHERA TPS | Private Sector | Uttar Pardesh | NR | Steam | 1 | 45 | 2011-11-06 | 5.6329 | COAL | N | Y | Y | Y |  | 30/09/2021 |  | ESP UPGRADATION/ CFBC BOILER
14 | Bajaj Power Co | BARKHERA TPS | Private Sector | Uttar Pardesh | NR | Steam | 2 | 45 | 2012-01-28 | 5.4055 | COAL | N | Y | Y | Y |  | 31/03/2021 |  | ESP UPGRADATION/ CFBC BOILER
15 | Bajaj Power Co | KHAMBARKHERA TPS | Private Sector | Uttar Pardesh | NR | Steam | 1 | 45 | 2011-10-17 | 5.6877 | COAL | N | Y | Y | Y |  | 30/09/2021 |  | ESP UPGRADATION/ CFBC BOILER
16 | Bajaj Power Co | KHAMBARKHERA TPS | Private Sector | Uttar Pardesh | NR | Steam | 2 | 45 | 2011-11-28 | 5.5726 | COAL | N | Y | Y | Y |  | 30/09/2021 |  | ESP UPGRADATION/ CFBC BOILER
17 | Bajaj Power Co | KUNDARKI TPS | Private Sector | Uttar Pardesh | NR | Steam | 1 | 45 | 2012-01-10 | 5.4548 | COAL | N | Y | Y | Y |  | 30/09/2021 |  | ESP UPGRADATION/ CFBC BOILER
18 | Bajaj Power Co | KUNDARKI TPS | Private Sector | Uttar Pardesh | NR | Steam | 2 | 45 | 2012-02-29 | 5.3178 | COAL | N | Y | Y | Y |  | 31/03/2021 |  | ESP UPGRADATION/ CFBC BOILER
19 | Bajaj Power Co | MAQSOODPUR TPS | Private Sector | Uttar Pardesh | NR | Steam | 1 | 45 | 2011-11-03 | 5.6411 | COAL | N | Y | Y | Y |  | 30/09/2021 |  | ESP UPGRADATION/ CFBC BOILER
20 | Bajaj Power Co | MAQSOODPUR TPS | Private Sector | Uttar Pardesh | NR | Steam | 2 | 45 | 2012-01-21 | 5.4247 | COAL | N | Y | Y | Y |  | 31/03/2021 |  | ESP UPGRADATION/ CFBC BOILER
21 | Bajaj Power Co | UTRAULA TPS | Private Sector | Uttar Pardesh | NR | Steam | 1 | 45 | 2012-02-21 | 5.3397 | COAL | N | Y | Y | Y |  | 30/09/2021 |  | ESP UPGRADATION/ CFBC BOILER
22 | Bajaj Power Co | UTRAULA TPS | Private Sector | Uttar Pardesh | NR | Steam | 2 | 45 | 2012-03-19 | 5.2658 | COAL | N | Y | Y | Y |  | 31/03/2021 |  | ESP UPGRADATION/ CFBC BOILER
[5 empty] | TOTAL CAPACITY |  |  | 2030 MW
(22 Units)
YEAR-WISE PHASING PLAN
[8 empty] | YEAR | Capacity | Units
[8 empty] | 2019 | 250 | 2
[8 empty] | 2020 | 0 | 0
[8 empty] | 2021 | 720 | 12
[8 empty] | 2022 | 540 | 4
[8 empty] | 2023 | 270 | 2
[8 empty] | 2024 | 0 | 0
[8 empty] | Under Closure | 250 | 2
[8 empty] | Total | 2030 | 22